## Sheet1
| Suggested Action | Suggested Activities | Progress | How long? E.g. one day, a week etc | When? | [18 empty] | Responsibility | Notes
[5 empty] | 2014 | [9 empty] | 2015
[5 empty] | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Stage 1: Starting up - sharing ideas about how useful a Neighbourhood Plan might be | Getting started: Parish Council & Community Approval | Parish/Town Council meeting to discuss potential Neighbourhood Plan e.g. process, ideas, aspirations | Completed | bar: 2014 Mar
|  | Do pre-publicity/awareness raising with Parish residents - ensuring they know what is being discussed | Completed | bar: 2014 Mar
| Defining the Neighbourhood | Discuss the options and implications and a suggested Neighbourhood Area (i.e. area the the Neighbourhood Development Plan or Neighbourhood Development Order will cover) | Completed | bar: 2014 Mar
|  | Ensure that aims and objectives of doing the Neighbourhood Plan are clear/understood. | Ongoing | bar: 2014 Mar to 2015 Apr
Stage 2: Ensuring the community will support the neighbourhood planning process | Communication & Engagement Strategy | Stakeholder analysis to see who the main partners are in the process | bar: 2014 Apr to 2014 May
Develop communication and engagement strategy (what/who/how/when/why) | bar: 2014 Mar to 2014 May
Ensure that strategy is inclusive and accessible to all | bar: 2014 Apr
| General Awareness & Defining Key Issues and Opportunities | Information/awareness raising community event/s (based on communication and engagement strategy) | bar: 2014 Apr
Engage with local groups and people to gain their views on doing the neighbourhood plan, area, local issues and priorities e.g. short questionnaire | bar: 2014 May
Analyse questionnaire responses and gauge support and understanding of neighbourhood planning, broadly define key issues and priorities from responses | bar: 2014 May
Ensure events and questionnaire are inclusive | bar: 2014 Apr to 2014 May
Stage 3: Getting organised - making sure you're ready to prepare the plan | Set up Steering Group/Neighbourhood Planning Team | Set up Steering Group and agree roles (chair etc) and Terms of Reference | Completed | bar: 2014 Apr
|  | Agree and Set up process to ensure flow of information between Parish/Town Council and Steering Group. | Completed | bar: 2014 Apr
Consider if Steering Group would benefit from other representation e.g. outlying hamlets/villages
Consider Skills/knowledge/interests/representation of Steering Group | bar: 2014 Apr
|  | Check for inclusivity and diversity in the makeup of the Steering Group | Completed | bar: 2014 Apr
Populate Action Plan with time scales (for individual tasks & realistic timeframe for process) & resources (people/funding) etc | bar: 2014 Apr
Agree Action Plan | bar: 2014 Apr
| Submission of letter & map to DistrictCouncil | Parish/Town Council to send letter and map to District Council to formally apply for Neighbourhood Area | Completed | 8 - 10 weeks (as 6 week consultation period) | bar: 2014 Mar
|  | Districtl Council decision on request for Neighbourhood Area as submitted by Parish/Town Council | Completed | bar: 2014 Mar
|  | Disrict Council to formally advertise Neighbourhood Area | Completed | bar: 2014 Mar
|  | District Council decision following consultation period | Completed | bar: 2014 Mar
Stage 4: Information gathering - getting to know your neighbourhood and its context | Key Stakeholder Engagement ( ongoing) | Establish what interest there is from potential developers | bar: 2014 Apr
Discussions with landowners | bar: 2014 Apr
Ongoing liaison with key stakeholders | bar: 2014 Apr to 2015 May
| Building the Evidence Base (possibly 3-4 months) | Gather existing information e.g. demographic and socio-economic information, designated/protected sites, views from the initial questionnaire and community events | bar: 2014 Apr to 2014 Jun
Assess evidence gathered to identify gaps | bar: 2014 Apr to 2014 Jun
Establish what evidence is still required and where it may be sourced | bar: 2014 Jul
Source or produce additional evidence if required | bar: 2014 Jul
Undertake mapping exericise - e.g. infrastructure, trees and environmental elements, leisure facilities, shops, historical assets etc | bar: 2014 May to 2014 Jul
Undertake analysis of evidence | bar: 2014 Jul; 2014 Sep
SWOT analysis | bar: 2014 Jun to 2014 Jul
| In-depth Community Consultation (possibly 6 months?) | Hold community events to present various development options (ensuring landowners are on board) and feedback results from the initial questionnaire/engagement
Draft survey questions, this should be informed by the previous evidence gathering carried out through building the evidence base and the initial questionnaire
Agree dates (distribution/close), distribution method, consider incentive for completing questionnaire?
Ensure the questionnaire is inclusive and accessible to all
Distribute questionnaires
Collect completed questionnaires (if by hand)
Analyse questionnaire responses
Stage 5: Pulling it all together - what you want the neighbourhood to be like | Scope and content | Develop draft vision and aims for the Neighbourhood Plan
If an NDO, will it give full permitted development rights or 'in principle'?
How long will the plan stand for? How often should it be refreshed?
Review relevent local and national planning policies and guidance
Stage 6: Writing policies and identifying projects | Drafting the Plan (4 months?) | Identify key themes and issues for the Neighbourhood Plan
Examine development options in context of baseline information and public opinion
Identify sites for protecting/blocking development e.g. valuable community spaces
Consult and agree the preferred direction with landowners
Seek advice from District Council on other assessments that may be required, e.g. Strategic Environmental Assessment (SEA), Habitats Regulations Assessment, Environmental Impact Assessment, flood risk assessment etc
Decide plan layout, format, design etc
Draft planning policies and guidance
Consider alternatives
Carry out a Sustainability Check
Consider mitigation measures to alleviate negative impacts and maximise positive outcomes
Finalise draft planning policies
Compile draft Neighbourhood Plan
Check conformity with District Council's Local Plan
Consider in terms of equality and diversity
Proof read draft Neighbourhood Plan
Make any amendments
Finalise draft Neighbourhood Plan
Stage 7: Testing and approving the Neighbourhood Plan - making sure the plan works and signing it off | Pre-submission Consultation (at least 6 weeks) | Consult on draft Neighbourhood Plan to ensure it represents what the community want - also feedback on results from detailed questionnaire and demonstrate how the Neighbourhood Plan tackles the issues raised.
| Finalise Plan (possibly 1 month) | Make any amendments necessary following pre-submission consultation
Re-check against various assessments as necessary
Re-check general conformity with District Council's Local Plan
| Submission of Plan & Approval (30 weeks at least) | Submit the Neighbourhood Plan to DistrictCouncil. This must include a map and statement identifying the area, consultation statement, confirmation that it meets legal obligations, any other assessments required such as SA, EIA etc |  | Approximately 26 - 40 weeks (due to 6 week consultation period on draft, 8 - 12 weeks for independent examination and 8 - 12 weeks to organise and hold referendum)
District Council will review the Neighbourhood Plan and if it meets requirements, it will then be publicised for consultation
District Council submit for independent examination
Modify or not? ( District Council may make modifications to the Neighbourhood Plan before the referendum to ensure that it complies with the recommendations of the examiner's report)
If the Neighbourhood Plan has to be modified, details to be publicised
Referendum
ADOPTION OF PLAN (if all of the above is succesful)
Stage 8: Delivering and monitoring the plan | Delivery | Parish/Town Council to develop an Implementation Plan, e.g. working with developers to make it happen
Monitoring - decide on how to monitor progress against objectives and repirting back to the community